{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":21,"n_cols":5,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["任务名称","工期","开始时间","完成时间","联系人"]
["聊天基础功能-安卓",2,"2017-07-17","2017-07-18","俊钦"]
["聊天列表管理-安卓",1,"2017-07-19","2017-07-19","俊钦"]
["聊天基础功能(图片/拍照/定位/表情)-安卓",2,"2017-07-20","2017-07-21","俊钦"]
["底部发送礼物-安卓",4,"2017-07-22","2017-07-25","俊钦"]
["用户详情送礼-安卓",0.5,"2017-07-25","2017-07-25","俊钦"]
["聊天详情-安卓",1,"2017-07-26","2017-07-26","俊钦"]
["群组创建与管理-安卓",1,"2017-07-27","2017-07-27","俊钦"]
["群详情-安卓",1,"2017-07-28","2017-07-28","俊钦"]
["交易贴功能-安卓",5,"2017-07-29","2017-08-01","俊钦"]
["朋友圈功能-安卓",5,"2017-08-02","2017-08-06","俊钦"]
["朋友圈图片管理-安卓",2,"2017-08-07","2017-08-08","俊钦"]
["用户系统图片管理-安卓",0.5,"2017-08-08","2017-08-08","俊钦"]
["用户详情-安卓",1,"2017-08-09","2017-08-09","俊钦"]
["个人详情交易贴管理-安卓",1,"2017-08-10","2017-08-10","俊钦"]
["附近的人-安卓",1,"2017-08-11","2017-08-11","俊钦"]
["附近群-安卓",1,"2017-08-12","2017-08-12","俊钦"]
["分享-安卓",0.5,"2017-08-12","2017-08-12","俊钦"]
["微信支付宝支付-安卓",3,"2017-08-13","2017-08-15","俊钦"]
["投诉-安卓",1,"2017-08-16","2017-08-16","俊钦"]
["其它零散页面-安卓",5,"2017-08-17","2017-08-21","俊钦"]